## Summary
WhiteLine B2B defect retest
Current deployment checked against the 27 items remaining after the 02-Oct report
Status | Count | Metric | Count
Pass | 9 | Original remaining | 27
Fail | 11 | Now closed | 9
Partially Fixed | 4 | Still requiring action | 18
Need to Test | 3
Notes
Live site | https://white-line-b2b.vercel.app
Source report | WhiteLine_B2B_Test_Cases.xlsx - Defect Log.csv
Access limitation | The second supplied Owner credential did not sign in. Finance/Operations cases remain pending.
Safe testing | No user, service request, complaint or production record was created, deleted or deactivated.

## Retest Detail
Defect ID | 02-Oct status | Current status | Module | Method | Evidence | Next action
Def-006 | Need to Test | Need to Test | Access control | Live | Provided accounts are Admin and Owner. No Finance/Operations login was available. | Provide a Finance/Operations test login.
Def-007 | Need to Test | Need to Test | Access control | Live | Deactivated-user login could not be tested without a suitable disposable Finance/Operations account. | Provide a disposable Finance/Operations login.
Def-013 | Still Open | Pass | Contracts | Live | Create Request now offers Business Sedan, Economy Sedan and SUV from contract classes. | Close.
Def-015 | Fail | Fail | Invoices | Live | Paid invoice details still show Drivers Required and Vehicles Required as em dashes. | Backend must return service request quantities.
Def-018 | Still Open | Fail | Authentication | Live | Wrong password reloads Login, clears both fields and leaves no persistent error. | Keep form state and display a persistent error.
Def-019 | Still Open | Need to Test | Authentication | Live | Fake-email invalid OTP stays on OTP screen, but a valid-account invalid OTP was not run because it sends an email. | Approve OTP send to a valid test mailbox.
Def-021 | Still Open | Fail | Authentication | Live | Same live behavior as Def-018: no persistent wrong-credentials error. | Fix with Def-018/037.
Def-023 | Still Open | Pass | Service requests | Live | Affected request no longer shows Corporate Mobility; category is blank when server has no class. | Close.
Def-024 | Need to Test | Partially Fixed | Service requests | Live + code | UI only offers contract-matched classes. Server rejection of a tampered class was not submitted. | Run authorized negative API submission.
Def-025 | Still Open | Partially Fixed | Complaints | Live | Full unique complaint IDs now display. Older complaints still show Submitted By as em dash. | Backfill or define handling for legacy submitter data.
Def-028 | Fail | Fail | Invoices | Live | Company is correct, but driver and vehicle values remain em dashes. | Fix invoice detail mapping.
Def-030 | Still Open | Pass | Contracts | Live | JPG contract is labelled with a .jpg filename and type Image. | Close.
Def-031 | Still Open | Pass | Invoices | Live | Full invoice IDs are displayed and exact full-ID search returns the invoice. | Close.
Def-034 | Still Open | Pass | Service requests | Live | Empty notes show a neutral no-instructions message; dummy text is gone. | Close.
Def-035 | Still Open | Fail | Service requests | Live + code | Current form still has no past-start-date check and no minimum-driver validation. | Add client and server validation.
Def-036 | Still Open | Pass | Service requests | Live | Past approved request no longer shows Cancel Request. | Close.
Def-037 | Still Open | Fail | Authentication | Live | Wrong-password 401 still reloads Login and removes the message. | Fix shared auth error handling.
Def-038 | Still Open | Pass | Complaints | Live | Complaint created 01 Oct at 22:58 now shows 01 Oct 2026 - 22:58. | Close.
Def-039 | Still Open | Partially Fixed | Panels | Live | Escape closes Invoice and Complaint panels, but Contract panel remains open. | Add Escape handling to Contract panel.
Def-040 | Need to Test | Partially Fixed | Invoices | Live + code | PDF generator includes Subtotal and VAT (15%). Browser popup prevented visual PDF inspection. | Manually open the generated PDF once.
Def-041 | Still Open | Pass | Invoices | Live | Details now use INVOICE DATE and DUE DATE labels. | Close.
Def-042 | Still Open | Fail | Complaints | Live | Complaint details still expose both Cancel Complaint and Delete Complaint. | Confirm business rule and remove disallowed actions.
Def-044 | Fail | Pass | Authentication | Live | Unregistered email proceeds to generic OTP Verification instead of revealing that no account exists. | Close.
Def-045 | Fail | Fail | Invoices | Live | 29 Sept overdue invoice still shows unpaid and is counted in Due Soon. | Derive overdue status consistently in API and filters.
Def-046 | Fail | Fail | Notifications | Live + code | Notification click handler only marks read; it does not navigate to the related invoice. | Add entity-aware navigation.
Def-047 | Fail | Fail | Users | Code + access check | Create User still checks only 8-character length and does not validate full-name characters. Owner login failed. | Align password/name rules on client and server.
Def-048 | Fail | Fail | Service requests | Live | Past request SR-1788915874349-QU8UC remains pending. | Expire stale pending requests server-side.